## Requirements
Sr. No. | Items | Description
1 | Device Type | Desktop/Tablet/Mobile
2 | Uploading Blog | Upload the blog details with text description, image files, publisher name author name. Use dynamic uploding of image choosen anywhere from machine.
3 | Comments | Adding a comments in the form of text, image or both. Mention when people had commented.
4 | Nesting of comments | You are able to comment on other comments and ability to add image feature in it.
5 | Close the blog | If blog is closed then its in read only you can not comment on such blog.(Do not delete anything once entered)
5 | Service Call | Use Node JS for REST API calls.
5 | Storage | Store Collected data in JSON format and render it immediately when user wishes.

## Design Screens
Home Page
Writing a new Blog

## User Stories
Story Point | Task Details | Duration (hrs) | Start Date | End Date | Status
Desinging templates | Create design templates for Home Page | 3
| Create design templates for Create Blog Page | 4
| Create design templates for Blog Details Page. The sample is not provided here. | 4
Creating responsive design for Desktop, Mobile and Tablet | Create all three pages responsive by using media queries. | 24
Bind Data From JSON | Create Sample Data in JSON file | 2
| Display list of blogs on home page as per design templates | 6
| Bind Blog Detail page. | 12
| Bind Create Blog page with Validation | 15